## Control
KITALE NATIONAL POLYTECHNIC
EVALUATION REPORT ON THE EFFECTIVENESS OF ACTIONS TAKEN TO ADDRESS RISKS AND OPPORTUNITIES
ADMINISTRATION DEPARTMENT
Prepared by: Deputy Principal Administration
Issue Date: 1st October 2021

## Risk Register
SNO. | PROCESS | INTERESTED PARTIES & THEIR REQUIREMENTS | RISK DESCRIPTION | CAUSES | AREA OF IMPACT | RISK OWNER | IMPACT | LIKELIHOOD | RISK LEVEL | STRATEGY | EXISTING CONTROLS | ADDITIONAL CONTROLS | RESOURCES | TARGET DATE | RESIDUAL RISK
[15 empty] | IMPACT | LIKELIHOOD |  | RESPONSIBILITY | COMMENT(S)
1 | SECURITY | STAFF AND ALL STUDENTS | THEFT | OPEN BOUNDARIES, INCOMPETENT SECURITY STAFF, CORRUPTION, CARELESSNESS, MISAPPROPRIATION OF FUNDS POOR MOTIVATION ETC | OPERATION | SECURITY OFFICERS | 3 | 1 | 3 | REDUCE | ADEQUATE SECURITY CHECKS AND ROTATIONAL SECURITY PERSONNEL | ENHANCE SECURITY MEASURES BY INCREASING THE NUMBER OF OFFICERS AND ADDITIONAL TOOLS, MOTIVATE SECURITY OFFICERS WELL, CONSTRUCT A MODERN GATE AND APPLY STRINGENT MEASURES ON FINANCIAL ETHICAL CONDUCT BY ENHANCING ACCOUNTABILITY | YES | DEC. 2021 | 1 | 1 | 1 | DP. ADMINISTRATION | MEASURES PUT IN PLACE WERE EFFECTIVE SINCE THE RISK IMPACT REDUCED BY 2 HOWEVER, THE RISK STILL EXISTS AND IT WAS CARRIED FORWARD TO THE RISK REGISTER FOR THE FY 2021-2022 FOR FURTHER TREATMENT
2 | TRANSPORT | ALL STAFF AND ALL STUDENTS | ACCIDENT DURING TRIPS | LONG WORKING HOURS BY DRIVERS, INADEQUATE REPAIRS AND MAINTAINANCE, CARELESS ROAD USERS SUCH AS DRUNKARDS AND DISODERLY, LOW QUALITY SPARE PARTS ETC | HEALTH AND SAFETY | TRANSPORT MANAGER | 1 | 3 | 3 | TRANSFER | ADEQUATE REPAIRS AND MAINTAINANCE | ORGANIZE FOR TRAINING OF THE TRANSPORT MANAGER, RECRUIT MORE STAFF | YES | DEC. 2021 | 1 | 1 | 1 | REGISTRAR ADMINISTRATION | THE MEASURE WAS EFFECTIVE SINCE THE RISK REDUCED THE LIKELIHOOD BY 2 HOWEVER, THE RISK STILL EXISTS AND IT WAS CARRIED FORWARD TO THE RISK REGISTER FOR THE FY 2021-2022 FOR FURTHER TREATMENT
3 | REPAIRS AND MAINTAINANCE | ALL STUDENTS AND ALL STAFF | OBSOLETE EQUIPMENT | OUTDATED EQUIPMENT/MACHINE | OPERATIONAL | REPAIRS AND MAINTAINANCE OFFICER | 1 | 5 | 5 | AVOID | TRY TO TALLY THEM TO THE OBJECTIVE | DISPOSE AND GET THE MODERN EQUIPMENTS | YES | DEC. 2021 | 1 | 3 | 3 | REGISTRAR ADMINISTRATION | THE MEASURE WAS EFFECTIVE SINCE THE RISK REDUCED THE LIKELIHOOD BY 2 HOWEVER THE RISK IS STILL ANTICIPATED SINCE ITEMS BECOME OBSOLETE REGULARLY. THE RISK WAS CARRIED FORWARD TO THE RISK REGISTER FOR THE FY 2021-2022 FOR FURTHER TREATMENT
| ACADEMIC | INDUSTRY, STUDENTS, PARENTS, GOVERNMENT AND MANAGEMENT | FAILURE TO COMPLETE THE SYLLABUS ON TIME | INADEQUATE REOURSES, FINANCIAL ISSUES ON STUDENTS | CURRICULUM | DP. ADMIN AND | 3 | 2 | 6 | MITIGATE THE RISK LEVEL | RESOURCE PLANNING, SPONSORSHIP | HAVING MECHANISMS TO COLLECT FEES ON TIME, ENSURE SYLLABUS COVERAGE, GETTING RESOURCES ON TIME | YES | DEC. 2021 | 2 | 1 | 2 | DP. ACADEMICS | FEE COLLECTION MECHANISM WAS EFFECTIVE AND SYLLABUS COVERAGE HAS IMPROVED DESPITE THE OTHER RISK OF DISEASE OUTBREAK SUCH AS COVID 19. THEREFORE THE RISK STILL REMAINS BUT MITIGATED TO A LESSER LEVEL.THEREFORE, THE RISK STILL EXISTS AND IT WAS CARRIED FORWARD TO THE RISK REGISTER FOR THE FY 2021-2022 FOR FURTHER TREATMENT

## Opportunities Assessment
OPPORTUNITIES ASSESSMENT
# | ISSUES | OPPORTUNITIES | ACTION | TIMELINES | RESOURCES | RESPONSIBILITY | STATUS | COMMENTS
1 | SECURITY | PROVISION OF SECURITY PERSONNEL BY GOVERNMENT, USE OF MODERN TECHNOLOGY | REQUEST FOR SECURITY REINFORCEMENT FROM THE GOVERNMENT | ACHIEVED | AVAILABLE | DP. ADMINISTRATION | SECURITY AVAILABLE BUT MORE STILL NEEDED | EFFECTIVELY ACHIEVED AND STILL THE PROCESS IS CONTINOUS
2 | CUSTOMER COMPLAINTS | PROVISION OF TRAINING STAFF ON CUSTOMER RELATIONS | CAPACITY BUILDING, ANALYSIS OF CUSTOMER FEEDBACK TOOL | ACHIEVED | AVAILABLE | REGISTRAR ADMINISTRATION | TRAINING CONDUCTED BUT MORE STILL REQUIRED | THE OPPORTUNITY WAS EFFECTIVELY UTILISED AND IS STILL CONTINOUS
3 | INADEQUATE MACHINES/ EQUIPMENT | GRANTS FROM GOVERNEMENT AND NON GOVERNEMENTAL ORGANIZATIONS | PURCHASE MORE MACHINES/EQUIPMENT | ACHIEVED | AVAILABLE | DP. ADMINISTRATION | MACHINES AND EQUIPMENT AVAILABLE | MACHINES PURCHASED HOWEVER INDUSTRY NEEDS STILL DEMANDS MORE SO THE POLYTECHNIC STILL REQUIRES TO PURCHASE MORE