## Control
KITALE NATIONAL POLYTECHNIC
RISK REGISTER AND OPPORTUNITY ASSESSMENT DOCUMENT - OFFICE OF CBET COORDINATOR
Doc No.:KNP/RR&OAD/CBET/003
Version: C
Revision: 1
Prepared/Reviewed by: CBET Coordinator Signature………………………………......
Approved by: Principal Signature…………………………………….
Issued by: Management Representative Signature……………………………………….
Issue date: 25th October 2021

## Risk Register
SNO. | PROCESS | INTERESTED PARTIES & THEIR REQUIREMENTS | RISK DESCRIPTION | CAUSES | AREA OF IMPACT | RISK OWNER | IMPACT | LIKELIHOOD | RISK LEVEL | STRATEGY | EXISTING CONTROLS | ADDITIONAL CONTROLS | RESOURCES | TARGET DATE | RESIDUAL RISK |  |  | RESPONSIBILITY
[15 empty] | IMPACT | LIKELIHOOD | RISK LEVEL
1 | Curriculum Implementation | All stakeholders | Negative attitudes on CBET Programs | Low sensitisation Activities and fear of new programs | Operations and Implementations | CBET COORDINATOR | 5 | 5 | 25 | Reduce the risk. | Low sensisation and marketing activities | Increase CBET sensitisation and marketing Activities | Personnel, Finance, Stationery, Funds. | June, 30th 2022
2 | Curriculum Implementation | All Stakeholders | Non effective Marketing Strategy | Fear of unknown and lack of proper information | Implementation | CBET COORDINATOR | 4 | 3 | 12 | Reduce the risk. | None | Modify the marketing strategies. | Personnel, Finance, Stationery, Funds. | June, 30th 2022
3 |  | All stakeholders | status squo to remain | Resistance to change | implementation | CBET COORDINATOR | 3 | 3 | 9 | Reduce the risk. | none | Sensitization, attention by the top management, QMS review | Personnel, Finance, | June, 30th 2022
4 | Curriculum Deveoplment | All stakeholders | Cost of carrying out needs assessemnt | Inadequate needs assessment | curriculum development | CBET COORDINATOR | 4 | 3 | 12 | Reduce the risk. | None | Monitor to ensure it doesn’t occur | Personnel, Finance, | June, 30th 2022
5 | Curriculum Deveoplment | All stakeholders | Technical skills needed to develop curriculums | Inadequate technical skills and Knowledge | curriculum development | CBET COORDINATOR | 3 | 2 | 6 | Reduce the risk. | None | Monitor to ensure it doesn’t escalate | Personnel, Finance, | June, 30th 2022

## Opportunities Assessment
OPPORTUNITIES ASSESSMENT
# | ISSUES | OPPORTUNITIES | ACTION
1 | Review of Standard | Train staff | Engage a consultant to train existing and newly appointed staff on the new std
2 | Contract with the certifying body | adherence to the budget | top management commits to provision of finances