## Control
KITALE NATIONAL POLYTECHNIC
RISK REGISTER & OPPORTUNITY ASSESSMENT DOCUMENT -ACADEMIC DEPARTMENT
Doc No.: KNP/RR&OA/AD/003
Version: C
Revision: 0
Prepared/Reviewed by: Heads of Academic Departments
Approved By: The principal
Issue Date: 1ST October 2021

## Risk Register
SNO. | PROCESS | INTERESTED PARTIES & THEIR REQUIREMENTS | RISK DESCRIPTION | CAUSES | AREA OF IMPACT | RISK OWNER | IMPACT | LIKELIHOOD | RISK LEVEL | STRATEGY | EXISTING CONTROLS | ADDITIONAL CONTROLS | RESOURCES | TARGET DATE | RESIDUAL RISK |  |  | RESPONSIBILITY | COMMENTS
[15 empty] | IMPACT | LIKELIHOOD | RISK LEVEL
3 | CURRICULUM IMPLEMENTATION PROCESSES | GUARDIAN/SPONSORS/PARENTS/STUDENTS/MOE | STUDENT DROPOUT | NEGATIVE ATTITUDE BY STUDENTS TOWARDS CERTAIN UNITS, CHRONIC FAILURE | OPERATIONAL | HOD | 2 | 3 | 6 | REDUCE | OFFER G&C ON ATTITUDE CHANGE AND CHOICE OF COURSE | PROVISION OF SPECIALISED TRAINING FOR SLOW LEARNERS, BENCHMARK WITH SISTER INSTITUTIONS, DEVELOP MOTIVATIONAL PROGRAMMES FOR MATHEMATICS, ENGINEERING AND SCIENCE RELATED UNITS. | PERSSONEL, FUNDS
4 | CURRICULUM IMPLEMENTATION PROCESSES | GUARDIAN/SPONSORS/PARENTS/STUDENTS/MOE | POOR SYLLABI COVERAGE | ABSENTISM BY LECTURERS, INADEQUATE TEACHING STAFF, OVERLOAD OF TEACHING WITH NON ACADEMIC RESPONSIBILITIES | OPERATIONAL | HOD | 2 | 3 | 6 | REDUCE | ANALYSIS OF WEEKLY ATTENDANCE TOOLS, RECORDS OF WORK, VERIFICATION OF SCHEMES OF WORK, ANALYSIS OF STUDENT FEEDBACK QUESTIONAIRE | SET UP MOTIVATION PROGRAMMES FOR TEACHING STAFF, PROPOSE TO MANAGEMENT FOR REDISTRIBUTION OF NON ACADEMIC RESPONSIBILITIES OF TEACHING STAFF, ACQUIRE MORE TEACHING STAFF. | PERSSONEL, FUNDS
5 | CURRICULUM IMPLEMENTATION PROCESSES | TRAINERS AND TRAINEES AND TECHNICIANS | PRACTICAL LESSONS RELATED INJURIES( BURNS,CUTS,SCALDS,SPRAINS,FRACTURES,SHOCKS,SAFFOCATIONS) | POOR WORKSHOP/LABORATORY/KITCHEN SETUP BY TECHNICIAN, NEGLIGENCE FROM TRAINEES AND TRAINERS, IGNORANCE BY TRAINEES, INADEQUATE LIGHTING | SAFETY | HOD | 3 | 4 | 12 | REDUCE | AVAILABILITY LABORATORY/WORKSHOP/KITCHEN SAFTY RULES | CONTINOUS TRAINING ON LABORATORY/WORKSHOP/KITCHEN SAFTY RULES, FREQUENT INSPECTION OF MATERIALS AND EQUIPMENTS, REPLACEMENT OF FAULTY EQUIPMENTS | PERSONNEL, FUNDS

## Opportunities Assessment
OPPORTUNITIES ASSESSMENT
# | ISSUES | OPPORTUNITIES | ACTION
1 | UNTAPPED CATCHMENT FOR TAILOR MADE PROGRAMMES | SET UP STRONG LEARNING PROGRAMMES | PROPOSE TO MANAGEMENT TO INTRODUCE FLEXIBLE LEARNING PROGRAMMES E.G DISTANCE LEARNING, EVENING AND WEEKEND PROGRAMMES.
2 | LACK OF CLEAR CURRICULA IN VARIOUS INDUSTRIES/ORGANIZATIONS | DEVELOP RESPONSIVE CURRICULA FOR INDUSTRIES/ORGANIZATIONS | PROPOSE TO MANAGEMENT TO SET UP INDUSTRY LINKS AND COLLABORATIONS TO DEVELOP AND REVIEW THEIR CURRICULA.