## Control
KITALE NATIONAL POLYTECHNIC
RISK REGISTER AND OPPORTUNITY ASSESSMENT DOCUMENT - RESEARCH AND DEVELOPMENT DEPARTMENT
Doc No.:KNP/RR&OAD/R&D/003
Version: C
Revision 1
Prepared/Reviewed by: Head of Research and Development Signature………………………………......
Approved by: Principal Signature…………………………………….
Issued by: Management Representative Signature……………………………………….
Issue date: 25th October 2021

## Risk Register
SNO. | PROCESS | INTERESTED PARTIES & THEIR REQUIREMENTS | RISK DESCRIPTION | CAUSES | AREA OF IMPACT | RISK OWNER | IMPACT | LIKELIHOOD | RISK LEVEL | STRATEGY | EXISTING CONTROLS | ADDITIONAL CONTROLS | RESOURCES | TARGET DATE | RESIDUAL RISK |  |  | RESPONSIBILITY
[15 empty] | IMPACT | LIKELIHOOD | RISK LEVEL
1 | TVET fairs and Exhibition/innovations | Government and agencies/public/KNP council/principal/KNP staff/students/FO/PO | Piracy | failure to register and protect innovations | legal regulatory | HOD | 3 | 3 | 9 | risk reduction | register innovations with KIPI or KECOBO | desist exhibition of innovations before protection | funds for patenting/copyrighting. Materials - stationery. Equipment -computers/printers/plotters | 30th June, 2022
|  |  | loss of innovations | insufficient monitoring measures | financial | HOD | 3 | 2 | 6 | risk reduction | develop innovation register for control | assign responsibility for monitoring innovations | funds, Materials - stationery. Equipment, personnel | 30th June, 2022
|  |  | damage of innovations | mishandling, insufficient fastening or packaging | financial | HOD | 3 | 2 | 6 | risk reduction | design innovations as knock down kit | apply safe handling techniques | funds, Materials - stationery. Equipment, personnel | 30th June, 2022
2 | Research and Survey | Government and agencies/public/KNP council/principal/KNP staff/students/FO/PO | Plagiarism | failure to observe professionalism in research | legal regulatory | HOD | 3 | 4 | 12 | risk reduction | review research licences and authority | vet, register and publish successful research papers | funds, Materials - stationery. Equipment, personnel | 30th June, 2022
|  |  | Lack of integrity | failure to observe professionalism in research | legal regulatory | HOD | 3 | 4 | 12 | risk reduction | review research licences and authority | monitor the research process and review the research results | funds, Materials - stationery. Equipment, personnel | 30th June, 2022

## Opportunities Assessment
OPPORTUNITIES ASSESSMENT
# | ISSUES | OPPORTUNITIES | ACTION
1 | Open opportunities for research to KNP fraternity | establish internal research paper conferences | make proposal for establishment of internal conference and identification of presenters.
2 | Exposure of staff to research activities | competitive sponsoring of KNP staff to external conferences | make proposal for funding by the polytechnic management