## Control
KITALE NATIONAL POLYTECHNIC
RISK REGISTER AND OPPORTUNITY ASSESSMENT DOCUMENT - GUIDANCE AND COUNSELLING DEPARTMENT
Doc No.:KNP/RR&OAD/G&C/003
Version: C
Revision 1
Prepared/Reviewed by: Head of Guidance and Counselling Signature………………………………......
Approved by: Principal Signature…………………………………….
Issued by: Management Representative Signature……………………………………….
Issue date: 25th October 2021

## Risk Register
SNO. | PROCESS | INTERESTED PARTIES & THEIR REQUIREMENTS | RISK DESCRIPTION | CAUSES | AREA OF IMPACT | RISK OWNER | IMPACT | LIKELIHOOD | RISK LEVEL | STRATEGY | EXISTING CONTROLS | ADDITIONAL CONTROLS | RESOURCES | TARGET DATE | RESIDUAL RISK |  |  |  | REMARKS
[15 empty] | IMPACT | LIKELIHOOD | RISK LEVEL | RESPONSIBILITY
1 | Counselling | students, teaching and non teaching staff | Non availabilty of services | heavy workload of the department staff, lack of branding | Reputational | G&C HOD | 1 | 5 | 5 | Avoid | counselling schedule and the availability ofcounsellorsand request for a minimun number of hours for the department members | management to hasten employee a full time counsellor for the polytechnic, require the members undertake a basic course in counselling | funds for refreshments, partial schoraship for the training of the department members as they undertake counselling course | 30/06/2022
2 | Training of peer counsellors | students, teaching and non teaching staff and the administartion | Lack of commitment of peers counselling others | Lack of time, recognition intimidation by other peers, failute of the PC being good role models, ensure all peer counsellors are branded | Reputational | G&C HOD | 1 | 5 | 5 | reduce | collecting the counselling documents at the end of every term | continuous training developing a schedule for peer counsellors on duty peer week and branding for visibility, weekly activity that touches on the issues affecting the polytechnic community and consinder training peer counsellors twice a year because of the increased numbers of the students and fluidity of the peer counsellors | funds for refreshments | 30/06/2022
2 | Training of peer groups | students, staff and non teaching staff | inability to disseminate correct information as expected | lack of training peer groups, lack of commitment to dissemination information | reputational | Principal, HOD G&C, other processes owners whose information is being disseminated | 1 | 5 |  | reduce | relying only on the peer counsellor to rely information | peer groups to be identified and build capacity, a sensitization schedule | funds for training | 30/06/2022
3 | Termly activities | students teaching and non teaching staff and administration | inability to carry out all the activities | inadequate funds, resources, change of the institution's calender of events | Reputational | G&C HOD Principal | 1 | 4 | 4 | reduce | adhere to the calender of events | management to avail adequate resources timely communication on the change of the termly calender of events review of the calender of events | funds | 30/06/2022

## Opportunities Assessment
OPPORTUNITIES ASSESSMENT
# | ISSUES | OPPORTUNITIES | ACTION
1 | Unavailability of reliable and competent counsellors and peer counsellors | opportunity to train | to engage the management on the need to undertake External and internal capacity building and mentoring programmes of both
|  | exchange programmes | the department members and the peer counsellors can have exchange programmes with other polytechnics or other institutions so as to build knowledge and capacity
2 | Quality of our services | innovation and creativity | encourage and support innovative and creative ways of reaching and helping the client