## Control
KITALE NATIONAL POLYTECHNIC
RISK REGISTER & OPPORTUNITY ASSESSMENT DOCUMENT - HUMAN RESOURCE DEPARTMENT
Doc No.: KNP/RR&OA/HR/003
Version: C
Revision: 0
Prepared/Reviewed by: Head of Human Resource
Approved By: The Principal
Issue Date: 19th October 2017

## Risk Register
SNO. | PROCESS | INTERESTED PARTIES & THEIR REQUIREMENTS | RISK DESCRIPTION | CAUSES | AREA OF IMPACT | RISK OWNER | IMPACT | LIKELIHOOD | RISK LEVEL | STRATEGY | EXISTING CONTROLS | ADDITIONAL CONTROLS | RESOURCES | TARGET DATE | RESIDUAL RISK
[15 empty] | IMPACT | LIKELIHOOD | RISK LEVEL | RESPONSIBILITY | COMMENTS ON THE EFFECTIVENESS OF ACTIONS TAKEN TO ADDRESS RISKS
1 | RECRUITMENT. | ADMINISTRATION, COMMUNITY,STUDENTS | EMPLOYMENT OF UNSKILLED STAFF | FORGERY FAVOURISM NEPOTISM | OPERATIONAL | HR | 4 | 5 | 20 | AVOID | HR POLICY | DEVELOP A COMPREHENSIVE RECRUITMENT POLICY AND IMPLEMENT IT | HUMAN AND FINANCIAL | 2018-12-31 | 2 | 3 | 6 | HR | THE RISK REDUCED FROM 20 TO 6. A POLICY WAS DEVELOPED AND THIS ACTION YIELDED POSITIVE RESULTS. HOWEVER, THE RISK STILL REMAINS AND IT WAS CARRIED FORWARD TO THE RISK REGISTER FOR THE FY 2021-2022 FOR FURTHER TREATMENT
2 | DISCIPLINARY | STAFF AND STUDENTS | POOR DELIVERY OF SERVICE | INDISPLINE OF STAFF( ADRUG ABUSE) STAFF UNREADINESS TO SERVICE ,UNWILLING TO PERFORM | OPERATIONAL -LEGAL | HR | 5 | 3 | 15 | AVOID | HR POLICY | DEVELOP A COMPREHENSIVE DISCIPLINE POLICY AND IMPLEMENT IT | HUMAN AND FINANCIAL | 2018-12-31 | 3 | 1 | 3 | HR | THE RISK REDUCED FROM 15 TO 3 INDICATING THAT THE ACTION OF DEVELOPING AND IMPLEMENTING A DISCIPLINE POLICY WAS EFFECTIVE. HOWEVER, THE RISK STILL REMAINS AND IT HAS CARRIED FORWARD TO THE RISK REGISTER FOR THE FY 2021-2022 FOR FURTHER TREATMENT
3 | DISCIPLINARY | COUNCIL STAFF | PILFERAGE OF POLYTECHNIC PROPERTY AND RESOURCES | INDISCIPLINE | REPUTATIONAL | HR | 4 | 1 | 4 | SHARE AND REDUCE | HR POLICY AND DISCIPLINARY POLICY | ENFORCE ADHERENCE TO RELEVANT POLICIES | HUMAN AND FINANCIAL | 2018-12-31 | 4 | 1 | 4 | HR | THE RISK REMAINED CONSTANT, THE STRATEGY OF REDUCING/SHARING WAS NOT REALIZED. THIS MEANS THE ACTION TAKEN WAS NOT EFFECTIVE. THE RISK WAS CARRIED FORWARD TO RISK REGISTER FOR THE FY 2021-2022 FOR PROPER MANAGEMENT
4 | RECRUITMENT. | ALL STAFF AND STUDENTS | WRONG PLACEMENT OF EMPLOYEES | UNCLEAR STRUCTURE | OPERATIONAL | HR | 4 | 3 | 12 | SHARE AND REDUCE | ORGANOGRAM | REVIEW AND IMPROVE THE ORGANOGRAM | MANAGEMENT | 2018-12-31 | 6 | 4 | 6 | MANAGEMENT/HR | ALTHOUGH THE RISK REDUCED FROM 12 TO 6, THE NEW VERSION OF THE ORGANOGRAM IS CONFUSING AND NOT EFFECTIVE.THE RISK WAS CARRIED FORWARD TO THE RISK REGISTER FOR THE FY 2021-2022 FOR FURTHER TREATMENT
AND

## Opportunities Assessment
OPPORTUNITIES ASSESSMENT
# | ISSUES | OPPORTUNITIES | STATUES | COMENTS | ACTION
1 | LACK OF SKILLS | TO TRAIN THE STAFF | A BUDGET IS ALLOCATED TO THE SAME | ATLEAST 4 STAFF BE TRAINED IN EVERY FINANCIAL YEAR | PROVIDE THE CAPACITY BUILDING DURING BUDGET
2 | ABUSE OF ALCOHOL AND DRUS | PROVIDE EDUCATION ON SIDE EFFECT OF OF DRUGS | A POSITION HAS BEEN ADVERTISED FOR A COUNSELLOR | STAFF AN STUDENTS BE INDUCTED ON THE IMPORTANTS OF A COUNSELOR AND THE OFFICE | EMPLOY A COUNSELLOR TO ADVICE AND EDUCATE ON EFFECTS OF ALCOHOL AND DRUGS