## Control
KITALE NATIONAL POLYTECHNIC
RISK REGISTER & OPPORTUNITY ASSESSMENT DOCUMENT -LIBRARY DEPARTMENT
Doc No.: KNP/RR&OA/LIB/003
Version: C
Revision: 0
Prepared/Reviewed by: Head of Library
Approved By: The Principal
Issue Date: 19th October 2017

## Risk Register
SNO. | PROCESS | INTERESTED PARTIES & THEIR REQUIREMENTS | RISK DESCRIPTION | CAUSES | AREA OF IMPACT | RISK OWNER | IMPACT | LIKELIHOOD | RISK LEVEL | STRATEGY | EXISTING CONTROLS | ADDITIONAL CONTROLS | RESOURCES | TARGET DATE | RESIDUAL RISK |  |  |  | COMMENTS
[15 empty] | IMPACT | LIKELIHOOD | RISK LEVEL | RESPONSIBILITY
1 | Acqusition process | Library users who require information materials. Library staff who are incharge of acquiring the information resources Procurement department who carry out the acquisition process | lack of adequate information materials | Unavailability of certain information materials locally | operational | HOD | 3 | 5 | 15 | Avoid | ordering books that are locally available, | Timely requisitions to provide enough time for importations by suppliers. | financial resources | 2018-12-30 | 3 | 3 | 9 | HOD | Acquisition is done on a timely manner.Although action was taken,the risk still exists and it was carried forward to the Risk Register for the FY 2021-2022 for further action.
2 | Library security process and weeding | Administration to provide enogh security personell and equipments, library staff to safeguard information materials and all library equipment, Library users:handle information resources with care and follow library procedures | theft and destruction of information materials and other library equipment. | Negligence by staff and users,collusion ,failure of security system | legal/educational, safety. | HOD and Librarian | 1 | 4 | 4 | reduce | CCTV, human resources ,monitoring and supervision of the processes | Installing automated security systems, enforcementand security inspection | financial | 2018-12-30 | 2 | 5 | 10 | Hod /Librarian | Failure to install an automated security system & CCTV has led to escalation of the risk.The risk was carried forward to the Risk Register for the FY 2021-2022 to allow more time for the action to be taken
3 | Processing of information materials process | Library staff who carry out the process and maintain records and library users who require adequately labeled and processed information resources to access | poor processing of information materials. | Lack of skills and negligence | operational and legal | Library staff | 1 | 2 | 2 | avoid | human resources | On job training and enforcement | financial | 2018-12-30 | 1 | 2 | 2 | library staff | The risk has remained the same because there was no training for staff.he risk was carried forward to the Risk Register for the FY 2021-2022 to allow more time for the action to be taken
4 | Circulation process | Library staff who carry out the process and library users who require access to the information resources. | poor public relations and lack of courtesy | Poor communication skills | operational, reputational. | Librarians | 1 | 4 | 4 | avoid | customer complaints book and suggestion box | Additional on the job training on public relations | financial, human resource | 2018-01-30 | 1 | 3 | 3 | library staff | Staff were sensitized during staff meetings thus reduced likelihood.However, the risk still exist and it was carried forward to the Risk Register for the FY 2021-2022 for further treatment
5 | Repair of information materials | Library staff incharge of the process ,procurement department to outsource the services when there is need. tenderers who carry out the process on behalf of the department. | destruction and loss of information resources during the process | poor handling, dishonest tenderers | legal,safetyand security | HOD | 3 | 2 | 6 | share and transfare | selecting reliable tenderers | Training staff on repar of information materials | financial resources | 2018-12-30 | 1 | 3 | 3 | HOD | Although the risk reduced from 6 to 3, reliable tenderers selected though staff are yet to be trained.Thus the action taken was not 100% effective.The risk was carried forward to the Risk Register for the FY 2021-2022 for further treatment
6 | Library membership | Administration, library staff, and library users. | non members admission into the library | Lack of identification and poor security controls and collusion. | operational,security. | Library staff | 4 | 2 | 8 | reduce | human resources | Acquiring automated member recognition sytsem | financial, security | 2018-12-30 | 4 | 5 | 20 | Top Management | the risk has escalated due to lack of student identification by most of the trainees.it was carried forward to the Risk Register for the FY 2021-2022 for further treatmentMore action need to be done.

## Opportunities Assessment
OPPORTUNITIES ASSESSMENT
# | ISSUES | OPPORTUNITIES | ACTION | status | comments
1 | lack of skill | opportunity to train | propose for capacity building and coaching programs | 0% | The proposed action was not implented
4 | Theft | opportunity to install an automated security system | propose for a purchase of an automated security sytem | 0% | the proposed action was not implemented