## Control
RISK REGISTER & OPPORTUNITY ASSESSMENT DOCUMENT -MANAGEMENT REPRESENTATIVE
Doc. No. xxxxxx/RR&OAD/MR/005
Version:C
Revision:1
Prepared/Reviewed by: Management Representative
Approved By:
Issue date:1st October 2021

## Risk Register
SNO. | PROCESS | INTERESTED PARTIES & THEIR REQUIREMENTS | RISK DESCRIPTION | CAUSES | AREA OF IMPACT | RISK OWNER | IMPACT | LIKELIHOOD | RISK LEVEL | STRATEGY | EXISTING CONTROLS | ADDITIONAL CONTROLS | RESOURCES | TARGET DATE | RESIDUAL RISK |  |  |  | RESPONSIBILITY
[15 empty] | IMPACT | LIKELIHOOD | RISK LEVEL | COMMENTS
1 | Internal Audit | All process owners | Non adherence to procedures | Lack of induction | Legal and Reputational | MR | 3 | 2 | 6 | Reduce the risk. | Audit timetable, audit program, sensitization | Train induct and sensitize process owners and induct new staff | Personnel, Finance, Stationery, Laptops, Projector, Printer, Room/s. | June, 30th 2018 | 3 | 2 | 6 | The risk remained constant. It was carried forward to the risk register for the FY 2021-2022 for proper diagnosis and treatment such as enhancing sensitization and induction | MR
2 | Internal Audit | All process owners | Uncooperative Auditees | Fear of audits | Reputational, Operational | MR | 2 | 4 | 8 | Reduce the risk. | None | Sensitize | Personnel, Finance, Stationery, Laptops, Projector, Printer, Room/s. | June, 30th 2018 | 2 | 1 | 2 | The risk reduced from 8 to 2. The control put in place was effective. However, the risk still exist and it was carried forward to the risk register for the FY 2021-2022 for further treatment | MR
3 | corrective action | All process owners | Recurrence of non conformities | resistance to change, inadequate identification of the root cause | Reputational | MR | 2 | 3 | 6 | Reduce the risk. | CAR, and CAN | Sensitization, attention by the top management, QMS review | Personnel, Finance, | June, 30th 2018 | 4 | 2 | 8 | The risk increased from 6 to 8, meaning, the actions taken were ineffective. It was carried forward to the risk register for the FY 2021-2022 for proper diagnosis and treatment such as enhancing sensitization of process owners/auditors | MR
4 | control of documented information | All process owners | un approved changes to the QMS | Failure to follow document review process | operational | MR | 2 | 2 | 4 | Reduce the risk. | IQA | Monitor to ensure it doesn’t occur | Personnel, Finance, | June, 30th 2018 | 2 | 2 | 4 | The risk remained constant. It was carried forward to the risk register for the FY 2021-2022 for proper diagnosis and treatment such as carrying out frequent update of document issue register | MR
5 | control of documented information | All process owners | retention of obsolete documents | failure to withdraw, | Legal and Regulatory | MR | 2 | 1 | 2 | Reduce the risk. | IQA | Monitor to ensure it doesn’t escalate | Personnel, Finance, | June, 30th 2018 | 3 | 1 | 3 | The risk increased from 2 to 3, meaning, the actions taken were ineffective. It was carried forward to the risk register for the FY 2021-2022 for proper diagnosis and treatment such as conducting frequent update of document legal and regulatory register | MR
6 | all processes | All process owners | Ineffective implementation of the QMS | Lack of induction | Operational | Process owner | 2 | 1 | 2 | Reduce the risk. | Induction of staff on the QMS requirements | Monitor to ensure it doesn’t escalate | Personnel, Finance, | June, 30th 2018 | 3 | 2 | 6 | The risk increased from 2 to 6, meaning, the actions taken were ineffective. It was carried forward to the risk register for the FY 2021-2022 for proper diagnosis and treatment such as enforcing adherence to QMS Reviews Schedules | MR

## Opportunities Assessment
OPPORTUNITIES ASSESSMENT
# | ISSUES | OPPORTUNITIES | ACTION | Timeline | Resources | Responsibility | Status | Comments
1 | Review of Standard | Train staff | Engage a consultant to train existing and newly appointed staff on the new std | 30th June 2021 | Financial, Stationary | Principal/MR | Done | Completed
2 | Contract with the certifying body | adherence to the budget | top management commits to provision of finances | 24th Sep 2021 | Fiancial | Principal/MR | In progress | Signed contract